## risk_register
risk_id | stage | risk | likelihood | impact | gross_rating | controls | residual_rating | owner | review_date | acceptance_authority | status
RISK-0001 | Stage 2 | Bristol final WPL licensing-scheme order-maker and statutory submitter route unresolved | high | critical | P0 | Stage 2D controls OBC progression and FBC member route; Stage 2I confirms final order-making and Secretary of State submission are not closed and adds mandatory decision-box signatory and Full Council trigger controls | high | Legal Review Agent | 2026-06-26 | Simulation Gate Authority | narrowed_open
RISK-0002 | Stage 2 | WECA MCA statutory role consent funding assurance or no-role dependency misstated | high | critical | P0 | Stage 2E controls strategic-context and conditional funding-assurance wording; Stage 2F controls that current scoped repo evidence does not identify WPL-specific transferred/concurrent WECA MCA order-making; Stage 2G bounded official ModernGov search did not locate formal WPL decision; Stage 2H classifies package-level funding and assurance triggers; no-role consent consultation-response and final funding dependency conclusions remain unresolved | high | WECA Governance Agent | 2026-06-26 | Simulation Gate Authority | narrowed_open
RISK-0003 | Stage 2 | DfT engagement confused with Secretary of State confirmation | low | major | P1 | Stage 2B role map distinguishes DfT engagement from Secretary of State confirmation; Stage 2J anchors statutory confirmation generic DfT business-case and TAG alignment and bounded GOV.UK search-control evidence; WPL-specific DfT process or response still required | low | Legal Review Agent | 2026-06-26 | Simulation Gate Authority | controlled_open
RISK-0004 | Stage 4 | Boundary and parking-base data absent before options appraisal | high | critical | P0 | Stage 4A creates boundary manifest templates topology QA rules parking-base methodology canonical inventory headers DPIA scope and enforcement-linkage controls but no authoritative boundary or inventory data exists | high | Spatial Data Agent | 2026-06-26 | Simulation Gate Authority | controlled_open
RISK-0005 | Stage 5 | OBC drafting begins before SOC-equivalent OAR ASR and ASST controls | medium | major | P1 | Stage 5A creates options OAR ASR ASST model-card uncertainty benefits transferability and reappraisal controls but no agreed ASR shortlist model output BCR VFM or OBC economic case exists | medium | Appraisal Guidance Agent | 2026-06-26 | Simulation Gate Authority | controlled_open
RISK-0006 | Stage 1 | Comparator claims overstate Nottingham transferability before evidence acquisition | medium | major | P1 | Comparator source acquisition and transferability matrix required | medium | Comparator Evidence Agent | 2026-06-25 | Simulation Gate Authority | open
RISK-0007 | Stage 4 | Licensing enforcement and appeals design omits statutory procedural controls | medium | major | P1 | Licence and enforcement schemas added; Stage 4A inventory to enforcement linkage control added; operating procedures PCN templates and service policy still required | medium | Operations Design Agent | 2026-06-26 | Simulation Gate Authority | open
RISK-0008 | Stage 1 | Governance chronology overstates update reports as approvals | low | major | P1 | Decision notices and minutes acquired; assumptions register and Stage 2D decision-route map block implementation consultation FBC order-making submission and preferred-scheme claims | low | Bristol Governance Agent | 2026-06-26 | Simulation Gate Authority | controlled_open
RISK-0009 | Stage 1 | Academic congestion evidence is unavailable after failed source acquisition | medium | major | P1 | Claim matrix must omit independent congestion-reduction claims until replacement evidence is acquired | medium | Comparator Evidence Agent | 2026-06-25 | Simulation Gate Authority | open
RISK-0010 | Stage 1 | Guidance landing pages are mistaken for complete TAG or Magenta Book source packs | medium | major | P1 | Source register labels landing pages and Stage 5A guidance-source requirements require individual TAG units databook source notes and VFM framework before method or VFM reliance | medium | Appraisal Guidance Agent | 2026-06-26 | Simulation Gate Authority | controlled_open
RISK-0011 | Stage 2 | Future agents overstate WECA MCA role because funding assurance context is scattered | medium | major | P1 | Post Stage 2H context packet bounded read rule Stage 2H trigger map and Stage 2L context packet control future WECA MCA drafting | low | Programme Orchestrator | 2026-06-26 | Simulation Gate Authority | controlled_open
RISK-0012 | Stage 2 | Future agents promote Stage 2 narrowing controls into OBC FBC consultation statutory submission or operations readiness because legal governance context is scattered | medium | major | P1 | Stage 2L mandatory context packet banned-claim list domain add-ons and subagent packet criteria control future legal governance statutory OBC FBC and consultation drafting | low | Programme Orchestrator | 2026-06-26 | Simulation Gate Authority | controlled_open
RISK-0013 | Stage 3 | Future agents overstate Stage 3A strategic controls as Strategic Case preferred-scheme package-selection benefit funding or consultation readiness | medium | major | P1 | Stage 3A control package strategic QA benefits attribution package funding assurance registers and gate report preserve no preferred scheme no selected package no benefits no WECA/MCA position and no OBC/FBC readiness | low | Strategic Case Review Agent | 2026-06-26 | Simulation Gate Authority | controlled_open
RISK-0014 | Stage 6 | Future agents overstate OBC templates or assembly placeholders as OBC approval consultation officer-review or statutory readiness | medium | major | P1 | Stage 6A OBC readiness control package section claim dependency registers no-go claim register active assembly block OBC QA and gate report preserve no assembled OBC no officer DOCX and no Stage 7 readiness | low | Integrated Case Review Agent | 2026-06-26 | Simulation Gate Authority | controlled_open
RISK-0015 | Stage 8 | Future agents overstate Stage 8A controls as consultation launch legal materials privacy accessibility analysis or authority readiness | medium | major | P1 | Stage 8A consultation control package validator no-go claims material suffix controls response schema stakeholder coverage and simulated reviews preserve no launch no material output no response data no privacy notice and no analysis readiness | low | Consultation Review Agent | 2026-06-26 | Simulation Gate Authority | controlled_open
RISK-0016 | Stage 9A | Public or officer summaries overstate readiness or drift from controlled registers | medium | major | P1 | Public-first README officer dashboard pitfalls register checks-and-balances register Nottingham lessons register and officer-pack QA preserve no-go wording and controlled IDs | low | Officer Assurance Agent | 2026-06-26 | Simulation Gate Authority | controlled_open
RISK-0017 | Stage 7A | Future agents treat OBC assurance controls as a passed OBC gate or proceed recommendation | medium | major | P1 | Stage 7A validator gate checklist decision-report control red-team packet and gate report preserve no OBC approval no proceed recommendation no officer DOCX and no consultation launch | low | Integrated Case Review Agent | 2026-06-26 | Simulation Gate Authority | controlled_open
RISK-0018 | Stage 10A | Future agents treat statutory dossier controls as a ready statutory submission or certified scheme order | medium | critical | P1 | Stage 10A validator component register submission no-go register statutory route memorandum control clause powers matrix and gate report preserve no statutory submission no certified order no DfT acceptance no completed consultation statement and no FBC | low | Legal Review Agent | 2026-06-26 | Simulation Gate Authority | controlled_open
RISK-0019 | Stage 11A | Future agents treat final gate controls as FBC approval statutory submission or implementation recommendation | medium | critical | P1 | Stage 11A validator final gate checklist assurance panel no-go register decision-report control red-team packet and gate report preserve no FBC approval no legal sign-off no Section 151 review no statutory submission and no implementation recommendation | low | Integrated Case Review Agent | 2026-06-26 | Simulation Gate Authority | controlled_open
RISK-0020 | Stage 12A | Public visibility is mistaken for public-body endorsement professional advice or WPL readiness | medium | major | P1 | Stage 12A README wording publication checklist no-go register scan register and public-release QA preserve the distinction between public access and approval | low | Public Release Review Agent | 2026-06-26 | Simulation Gate Authority | controlled
RISK-0021 | Stage 13A | Critical-path handover is mistaken for approved programme, spend authority, procurement authority or readiness to proceed | medium | major | P1 | Stage 13A work-package register blocker map 90-day plan handover no-go register and handover QA preserve planning-only status and open blockers | low | Handover Review Agent | 2026-06-26 | Simulation Gate Authority | controlled
RISK-0022 | Stage 14A | Source-note pilot is mistaken for complete evidence review or verified business-case claims | medium | major | P1 | Stage 14A coverage register no-go register source-note QA and source-note wording preserve source-use limits and keep ISS-0007 open | low | Evidence Librarian | 2026-06-26 | Simulation Gate Authority | controlled_open
RISK-0023 | Stage 14B | Public GitHub repository exposes real or detector-colliding token-like material in evidence files or archives. | medium | major | P1 | Stage 14B removes raw PDFs containing Power BI/Grafana detector collisions from the current tree, redacts extracted text, records source-register omission status, adds scripts/scan_secrets.py and wires make validate to secrets-qa. | medium | Public Release Review Agent | 2026-06-26 | Simulation Gate Authority | controlled_open
RISK-0024 | Stage 14C | Live history rewrite and force push disrupt existing clones branches pull requests or forks while still not guaranteeing hosted alert closure. | medium | major | P1 | Stage 14C dry-run controls were executed live in Stage 14D using force-with-lease, local all-history scan and fresh remote mirror scan; residual hosted alert forks caches and old clone risks remain tracked in RISK-0025. | low | Public Release Review Agent | 2026-06-26 | Simulation Gate Authority | controlled_superseded_by_stage_14d
RISK-0025 | Stage 14D | Post-rewrite users misinterpret repository-history remediation as GitGuardian closure, fork cleanup, cache purge or external token revocation. | medium | medium | P2 | Stage 14D completion report and Stage 14E hosted-alert disposition report record force-with-lease execution, local all-history scan, fresh remote mirror scan, GitHub secret-scanning disabled response, ggshield absence and explicit GitGuardian follow-up. | low | Public Release Review Agent | 2026-06-26 | Simulation Gate Authority | controlled_open_external_check_required
RISK-0026 | Stage 14E | Future readers mistake repository-side verification for hosted GitGuardian closure. | medium | medium | P2 | Stage 14E report records ggshield absence GitHub secret scanning disabled API response repo scans and explicit GitGuardian follow-up requirement. | low | Public Release Review Agent | 2026-06-26 | Simulation Gate Authority | controlled_open_external_check_required