Bristol Workplace Parking Levy

OBC Risk, Process And Control Summary

Support document for the Stage 33A OBC simulation release and Stage 35A DOCX pack

Document type: Risk and process support summary

Status: Simulation-only editable DOCX

Date: 2026-06-27

Pack stage: Stage 35A DOCX document pack

Read this first This document is part of a shareable DOCX pack generated from the public Bristol WPL simulation repository. It is not a Bristol City Council document, not legal advice, not officer advice, not consultation material, not procurement authority and not an approved OBC.

# Current gate position

Current no-go position The simulation remains no-go for approval, consultation, OBC reliance, FBC reliance, procurement authority and statutory submission. The DOCX pack changes format only; it does not close any evidence or authority gap.

# Priority blockers

| ID | Stage | Severity | Issue |
| --- | --- | --- | --- |
| ISS-0001 | Stage 2 | P0 | Bristol final WPL licensing-scheme order-maker and statutory submitter route is unresolved |
| ISS-0002 | Stage 2 | P0 | WECA/MCA current-law role is unresolved after 2026 changes and cannot be inferred from strategy assurance scoped transferred-function silence or bounded public-search absence |
| ISS-0003 | Stage 4 | P0 | Authoritative WPL boundary and workplace parking inventory are absent |
| ISS-0004 | Stage 5 | P0 | No agreed ASR OAR ASST completed model cards model outputs or decision-grade uncertainty analysis exist |
| ISS-0005 | Stage 1 | P1 | Independent Nottingham congestion source SRC-ACADEMIC-0001 failed acquisition and cannot support congestion impact claims |
| ISS-0006 | Stage 4 | P1 | Licensing enforcement and appeals procedure is not populated despite new schemas |
| ISS-0007 | Stage 1 | P1 | Source notes for acquired priority evidence are not yet written |
| ISS-0008 | Stage 2 | P1 | DfT engagement classification remains to be evidenced even though Secretary of State confirmation route is controlled |
| ISS-0009 | Stage 3 | P1 | Package and cost-line funding assurance classification table is not populated because candidate packages are not yet defined |
| ISS-0010 | Stage 2 | P1 | Future agents need bounded context controls before legal governance statutory OBC FBC consultation DfT WECA MCA or order-change drafting |
| ISS-0011 | Stage 6 | P1 | OBC section evidence assembly and Stage 7 assurance are not complete |
| ISS-0012 | Stage 8 | P1 | Consultation launch material production privacy accessibility stakeholder coverage and response analysis readiness are not complete |
| ISS-0013 | Stage 9A | P1 | Public and officer documentation can drift from controlled registers or overstate simulation readiness |
| ISS-0014 | Stage 7A | P1 | OBC assurance gate controls exist but no OBC gate evidence packet or proceed recommendation exists |

# Priority risks

| ID | Stage | Rating | Risk | Residual |
| --- | --- | --- | --- | --- |
| RISK-0001 | Stage 2 | P0 | Bristol final WPL licensing-scheme order-maker and statutory submitter route unresolved | high |
| RISK-0002 | Stage 2 | P0 | WECA MCA statutory role consent funding assurance or no-role dependency misstated | high |
| RISK-0003 | Stage 2 | P1 | DfT engagement confused with Secretary of State confirmation | low |
| RISK-0004 | Stage 4 | P0 | Boundary and parking-base data absent before options appraisal | high |
| RISK-0005 | Stage 5 | P1 | OBC drafting begins before SOC-equivalent OAR ASR and ASST controls | medium |
| RISK-0006 | Stage 1 | P1 | Comparator claims overstate Nottingham transferability before evidence acquisition | medium |
| RISK-0007 | Stage 4 | P1 | Licensing enforcement and appeals design omits statutory procedural controls | medium |
| RISK-0008 | Stage 1 | P1 | Governance chronology overstates update reports as approvals | low |
| RISK-0009 | Stage 1 | P1 | Academic congestion evidence is unavailable after failed source acquisition | medium |
| RISK-0010 | Stage 1 | P1 | Guidance landing pages are mistaken for complete TAG or Magenta Book source packs | medium |
| RISK-0011 | Stage 2 | P1 | Future agents overstate WECA MCA role because funding assurance context is scattered | low |
| RISK-0012 | Stage 2 | P1 | Future agents promote Stage 2 narrowing controls into OBC FBC consultation statutory submission or operations readiness because legal governance context is scattered | low |
| RISK-0013 | Stage 3 | P1 | Future agents overstate Stage 3A strategic controls as Strategic Case preferred-scheme package-selection benefit funding or consultation readiness | low |
| RISK-0014 | Stage 6 | P1 | Future agents overstate OBC templates or assembly placeholders as OBC approval consultation officer-review or statutory readiness | low |

# High-materiality evidence gaps

| ID | Stage | Gap | Status |
| --- | --- | --- | --- |
| EG-0001 | Stage 1 | current amended legal texts and commencement/prospective amendment status not yet acquired | partially_closed |
| EG-0003 | Stage 2 | WECA/MCA formal role not yet verified against current constitutional/devolution material | partially_closed |
| EG-0005 | Stage 4 | Spatial boundary parking inventory and data-sharing sources not yet acquired | open |
| EG-0010 | Stage 2 | WECA/MCA current constitution delegations and meeting records require final role classification | partially_closed |
| EG-0011 | Stage 2 | West of England devolution and transport function instruments not yet verified for WPL powers | partially_closed |
| EG-0012 | Stage 1 | current official Green Book DfT transport business case TAG VfM and WECA assurance guidance snapshots not yet acquired | partially_closed |
| EG-0013 | Stage 5 | reappraisal triggers for guidance data costs revenues benefits design boundary charge consultation procurement and model validation not yet defined | partially_closed |
| EG-0014 | Stage 4 | authoritative boundary input package and spatial licences not yet acquired | open |
| EG-0016 | Stage 4 | DPIA lawful basis and information-governance pack for employer premises inspection VRM and enforcement data not yet complete | partially_closed |
| EG-0019 | Stage 2 | Bristol City Council authority-status and internal WPL order-making route not yet mapped | partially_closed |
| EG-0020 | Stage 2 | identity of body submitting initial order for Secretary of State confirmation not yet verified | open |
| EG-0021 | Stage 2 | current DfT and Secretary of State non-statutory evidence expectations not yet verified | partially_closed |
| EG-0023 | Stage 4 | licensing and enforcement operating procedure not yet populated against the 2009 Regulations | open |
| EG-0027 | Stage 3 | strategic problem definition baseline objectives stakeholder evidence and theory of change are not yet evidenced | open |

# OBC gate checklist summary

| Gate item | Assurance area | Status | Gate effect |
| --- | --- | --- | --- |
| OBC-GATE-001 | legal_governance | blocked_control_only | P0 |
| OBC-GATE-002 | strategic_case | blocked_control_only | P1 |
| OBC-GATE-003 | economic_appraisal | blocked_control_only | P0 |
| OBC-GATE-004 | spatial_parking | blocked_control_only | P0 |
| OBC-GATE-005 | financial_affordability | blocked_control_only | P1 |
| OBC-GATE-006 | commercial_operations | blocked_control_only | P1 |
| OBC-GATE-007 | management_delivery | blocked_control_only | P1 |
| OBC-GATE-008 | consultation_readiness | blocked_control_only | P1 |
| OBC-GATE-009 | equality_data_accessibility | blocked_control_only | P1 |
| OBC-GATE-010 | statutory_route | blocked_control_only | P0 |
| OBC-GATE-011 | red_team | blocked_control_only | P1 |
| OBC-GATE-012 | officer_editability | blocked_control_only | P1 |

# Process trail

| Stage | Purpose | Main output |
| --- | --- | --- |
| Stage 32A | WECA-style OBC simulation drafting. | Simulated working draft and exemplar corpus. |
| Stage 33A | Release the editable OBC simulation separately from the blocked assembled path. | Simulation release Markdown and gate report. |
| Stage 34A | Adopt a bounded GOV.UK-style writing skill. | Public/officer writing-control skill and no-overclaim checks. |
| Stage 35A | Create an officer-friendly DOCX pack. | DOCX files and ZIP package for sharing. |

# Next proof needed before real reliance

Source-supported Bristol final order-maker, submitter and signatory route.

Current-law WECA/MCA role and funding-dependency disposition.

WPL-specific DfT process or logged DfT response.

Authoritative boundary, workplace parking inventory and displacement evidence.

OAR, ASR, ASST, model outputs, BCR and VFM category.

Consultation launch authority, materials, privacy, accessibility and response-analysis route.

Real legal, finance, modelling, equalities, data, commercial, consultation and officer review.